## Make a Copy
Phase | Task | Owner/Lead | Due Date MM/DD/YY | Status | Notes
This is column indicates the phase of the project, usually in order of completion. | This column lists all of the core tasks required to successfully complete each phase towards moving onto the next one and achieving the team's goals. | This indicates the lead person responsibile for oversight and/or completion of this task. There could be more than one lead in cases where it's necessary. It is useful to note this for accountability. | Use this column to set incremental deadlines throughout your project for each task. | Indicate whether this task has been completed, in-progress or on-going. In-progress means that it has been started but not completed. On-going indicates that this is a tasks that will continue to be completed until the very end of the project. | Insert links to documents or comments if clarification or additional action is required for other team members. However, have a direct conversation via a meeting or email regarding any new items that the team has not previously dicussed.
Group Formation | Set goals, norms, and expectations | All | 2021-11-09 | Complete | Meet bi-weekly on Mondays, and Fridays
| Complete team contract | All | 2021-11-09 | Complete | 1. Adds names and signatures to Contract 2. Add goals and guidelines to contract
Logistics | Create shared Google Folder in the Google Team Drive | All | 2021-11-09 | Complete | Folder in "shared with me" on Drive
| Update Project Outline | All | 2021-11-09 | Complete | Assign duties for the project
Proposal Project | Background | Luxsika, Adrian, Evan | 2021-11-17 | Complete | Cover background of chosen product. Introduce product, discuss function, and problem being solved. Discuss why problem is worth solving. Discuss why current situation is not ideal. Discuss why solution is not ideal and is not Covid friendly.
| Proposed Project | Kartike, Tejveer, Bilal | 2021-11-17 | Complete | Discuss product that will be reversed engineered, and show off any prototype/early designs being planned
| Milestones with dates & division of work | Hamza, Joaquin, Emmily | 2021-11-17 | Complete | Talk about how we divided work, and talk about our meeting schedule. *note for division of work section we could add a screen shot of the project outline
| References | All | 2021-11-17 | Complete | Store all online sources
Final Report | Abstract | Kartike, Evan | 2021-11-21 | Complete | Abstract: breif summary of report
| Introduction (High level summary) | Kartike, Luxsika, Emmily | 2021-11-21 | Complete | Intro: discuss function, and problem being solved
| Background (more details on the engineering aspect) | Bilal, Hamza, Tejveer | 2021-11-21 | Complete | Background: explain product being reverse engineered. Explain function in more detail, discuss history of product, how it works and what it is made of (provide a diagram)
| Evaluation section 1: (durability, sustainabillity, performance) | Evan, Adrian, Hamza | 2021-11-21 | Complete | Evaluation: evalulate how the product works based on criteria (durability, sustainability)
| Evaulation section 2: (UX, profitability, affordability & accessibility, public good) | Adrian,Bilal, Joaquin | 2021-11-21 | Complete | Evaluation: evalulate how the product works based on criteria (durability, sustainability)
| Re-Design Proposal | All | 2021-11-21 | Complete | Talk about how we are going to improve upon the product in terms of features
| 3 iterations | All | 2021-11-21 | Complete | 3 iterations: explain how each design was made and changed, use visual aids
| 1st iteration | Luxsika, Evan, Kartike | 2021-11-19 | Complete
| 2nd iteration | Bilal, Adrian, Emmily | 2021-11-20 | Complete
| 3rd iteration | Hamza, Joaquin, Tejveer | 2021-11-21 | Complete
| Marketing | Kartike, Luxsika, Emmily | 2021-11-21 | Complete | Create a piece of marketing
| Refrences | All | 2021-11-21 | Complete | Store all online sources
Presentation | Introduction | Kartike, Luxsika, Emmily | 2021-11-23 | In-progress | Introduce our product it's function, and purpose
| Background | Bilal, Hamza, Tejveer | 2021-11-23 | In-progress | discuss product being reversed engineered | Bilal
| Current-uses | Evan, Adrian , Joaquin | 2021-11-23 | In-progress | Talk about what our product can be used for
| limitations | Bilal, Hamza, Tejveer | 2021-11-23 | In-progress | Talk about how our product was effected about Covid-19 and how it limits it
| 1st iteration | Luxsika, Evan, Kartike | 2021-11-23 | In-progress |  | evan
| 2nd iteration | Bilal, Adrian, Emmily | 2021-11-23 | In-progress |  | adrian
| 3rd iteration | Hamza, Joaquin, Tejveer | 2021-11-23 | In-progress
Feedback | Complete peer feedback survey | All | 2021-11-24 | In-progress